## Sheet1
引用编号 | 版本 | 冲刺号 | 分类 | 标题 | 故事 | 类型 | 进度 | 初始估计（h） | 优先级 | 如何演示 | 商业价值 | 理想时间（h） | 调整因子 | 复杂度 | 信息度 | 备注
1 | 1 | 1 | user story | 购物选择 | 作为京东顾客，我希望 能够在京东中搜索到更多 的意向商品选项，以便于 我能够有更好的比较选择 | Initial Feature | Not Done | 1 | 90 |  |  | 1
2 | 1 | 1 | user story | 提示商家发货 | 作为京东顾客，我希望 每次购物后都能给商家提 示最快发货，这样我就能 尽快的收货 | Initial Feature | Not Done | 1 | 89 |  |  | 1
3 | 1 | 1 | user story | 邮递详情 | 作为京东顾客，我希望购物 后能够实时查看邮件的订单状 态，以便于我能够追踪到当前 物件的邮递详情 | Initial Feature | Not Done | 3 | 91 |  |  | 3
4 | 1 | 1 | user story | 会员优惠领取 | 作为京东会员，我希望能够 领取更多的优惠卷，这样我就 可以节省商品购买费用 | Initial Feature | Not Done | 2 | 95 |  |  | 3
5 | 1 | 1 | user story | 快捷付款方式 | 作为京东会员，我希望付款时， 可以使用多种付款方式一起组合， 这样就能够方便我们付款 | Initial Feature | Not Done | 1 | 92 |  |  | 1
6 | 1 | 1 | user story | 会员返还更多京豆 | 作为京东会员，我希望能每次购 物后都能够返还更多的京豆，这样 促进我们的消费热情 | Initial Feature | Not Done | 2 | 95 |  |  | 3
7 | 1 | 1 | user story | 评价了解 | 京东会员，我希望收到商品后可 以对商品进行评价，以便于更多的 人可以了解这款商品 | Initial Feature | Not Done | 2 | 89 |  |  | 2
8 | 2 | 2 | user story | 商家优惠 | 作为京东商家，我希望系统推出有更多的免邮卷，可以促进消费者的消费 | Initial Feature | Not Done | 3 | 95 |  |  | 3
9 | 2 | 2 | user story | 会员优惠 | 作为京东会员，我希望在会员生日 当天能够有购物优惠，这样就能够使我 们会员有存在感，促进我们开心消费 | Initial Feature | Not Done | 2 | 93 |  |  | 2
10 | 2 | 2 | user story | 运营管理 | 作为京东运营商，我希望登陆时 可以用手机验证码登录，这样就 可以避免了客户忘记密码而不能登录 | Initial Feature | Not Done | 5 | 96 |  |  | 5
11 | 2 | 2 | user story | 运营管理 | 作为京东运营商，我希望有快速 退换货的通道，这样就能更好的 维护客户的消费权益 | Initial Feature | Not Done | 6 | 96 |  |  | 6
12 | 3 | 3 | user story | 客户要求 | 作为客户 ，我想要购物车功能 ， 以便我可以轻松地在线购买物品 | Initial Feature | Not Done | 5 | 96 |  |  | 5
13 | 3 | 3 | user story | 运营管理 | 作为京东运营经理 ，我想生成报告，以便我可以理解哪些部门需要更多资源 | Initial Feature | Not Done | 3 | 92 |  |  | 4
14 | 3 | 3 | user story | 客户需求 | 作为客户，我想在物品到 达时收到短信 ，以便我可以马上去接你 | Initial Feature | Not Done | 2 | 90 |  |  | 2
Note on A1: Luc Segers: This reference ID should be unique. This number is used throughout the whole worksheet so be aware.
Note on B1: Luc Segers: This is the release where the story will be developped
Note on C1: Luc Segers: This is the sprint where the story will be developped
Note on D1: Luc Segers: This is a category to which the story belongs. Example : Infrastrucuture, Back-End, Animation, ...
Note on F1: Luc Segers: This is the story (Feature, Epic, User). Depending on in which phase you are in (Présales, Scope, …) the detail could be higher. Normally you could describe a user story as follow: As a <Role> I can do <this> and the result is <that> ... Offcourse this is not always possible, so you should be creative. A story should conduct to the following rules: I = Independent N = Negotiable V = Valuable to customer E = Estimatable S = Small T = Testable
Note on G1: Luc Segers: Type of the story.
Note on H1: Luc Segers: Status of the story
Note on I1: Luc Segers: This column is calculated: Ideal Hours * Adjustment Factor
Note on J1: Luc Segers: M = Must Have S = Should Have C = Could Have W = Won't have this time
Note on L1: Luc Segers: 0 = Lowest Business Value 100 = Highest Business Value
Note on M1: Luc Segers: Enter here the new ideal estimates which are done with planningpoker
Note on N1: Luc Segers: This column is calculated based on the values of complexity and information. The data is looked up in the setup tab.
Note on O1: Luc Segers: Complexity 0 = Not Defined 1 = Very Simple 2 = Simple 3 = Moderate 4 = Complex 5 = Extreme Complex
Note on P1: Luc Segers: Information 0 = Not Defined 1 = No information 2 = Little information 3 = Moderate information 4 = Much information 5 = All information